## Sheet1
|  | Automation Plan | Automation Execution | Pending | (Reason)
May - 2st Week | Akshay | Tyre flow (Repair, Tyre transfer) | Not taken, working on claim | Repair, Tyre transfer | Working on the script review comments
| Vinutha | Tyre flow(Stock, script integration, Review) | Stock comp Script Integration comp, Review done EXTRA : Comp (Repair, tyre transfer,flat)
May - 4th Week | Akshay | Inventory flow(Distribute Items) | comp
| Vinutha | Inventory flow (Return Item) | In Progress | Return Item (JC Dispatch flow) | Jobcard flow is needed to script for this
May - 5th Week | Akshay | Recondition FLow(approve, dispatch) | comp
| Vinutha | Inventory flow (Return Item) | Comp
June 1st Week | Akshay | JC third & own party | In Progress | Own Party Pending
| Vinutha | JC Estimation Flow | In Progress | JC add mode is comp, Flow not taken
June - 2nd week | Akshay | Jobcard delivery Demo, JC credit bill, JC Dispatch | Jc Delivery Memo In progress, Jc credit bill& Dispatch not taken
| Vinutha | JC Estimation Approval, Vehicle Maintenance, Driver maintenance request | Comp with Integration
June - 3rd week | Akshay | Commit all scripting file and error solving | Scripting of flow is completed
| Vinutha | Exception handling and Complete script Integration | In Progress | T1 and T2 flow will run with a single command
June - 4th week | Akshay | All Flow Integration(jobcard, Inventory, Tyre) and commit files
| Vinutha | Exception handling and Complete script Integration
| Akshay | Plan of executing 42 flags from jc, Inventory, Tyre
2023-08-10 | Vinutha | Plan of executing 42 flags from jc, Inventory, Tyre

## Sheet4
|  | Automation Plan | Automation Execution | Pending | (Reason)
May - 4th Week | Akshay | Inventory flow(Distribute Items) | comp
| Vinutha | Inventory flow (Return Item) | In Progress | Return Item (JC Dispatch flow) | Jobcard flow is needed to script for this
May- 5th Wek | Akshay | Jobcard flow (own)
| Vinutha | Jobcard Estimation Flow, Inventory flow (Return Item)

## Sheet2
sl no | Flags | Resource | Status | Flag Detail sheet Status
1 | Allow Secondary trip ? | Vinutha | Done
2 | Invoice Numbering WorkOrder Wise? |  | Not Working
3 | Extra Tonnage Calculations? |  | Not Working | Need to discuss
4 | To Edit the S/C Freight Rate? |  | Not Working
5 | To Show Driver/Helper Batta? | Vinutha | Done
6 | Allow to Enter End Place and Party? | Vinutha | Done
7 | Show Customer Advance in T4 Tripsheet? |  | Not Working
8 | eSugam Details Yes/No |  | Not (particular cust) | Need to discuss
9 | Hrs For eSugam Expire |  | Not Working | Need to discuss
10 | Should allow to enter the same GC Number? (Yes/No) | Akshay | Done
11 | To Show Text in T4_TripSheet GC Template View |  | Not Working
12 | To Show Paid At Branch for S/C Payment in T4 Tripsheet? YES/NO | Vinutha | Done
13 | Allow User to Change Arrival after Bill Generation(CLC). | Vinutha | Done
14 | User Roles Who Can Add Description in T4 Tripsheet | Vinutha | Done
15 | Access Rights user roles to enter T4 Departure/Arrival KM. | Vinutha | Done
16 | Option to edit the Departure date and Departure km in arrival. | Akshay | Done
17 | Allow roles to Delete the Records in T4 Tripsheet | Vinutha | Done
18 | Allow roles to Delete Advances in T4 Tripsheet and Manage Trip Details |  | Not working
19 | Option to show Expenses Paid By Company yes or no for T1 and T4 tripsheet | Akshay | Done
20 | Access Rights to User Role to Change Billing Rate in T4 Arrival(Name , separated) | Vinutha | Done
1 | Invoice Numbering WorkOrder Wise? |  | Not Working
2 | Extra Tonnage Calculations? |  | Not Working | Need to discuss
3 | To Edit the S/C Freight Rate? |  | Not Working
4 | Show Customer Advance in T4 Tripsheet? |  | Not Working
5 | To Show Text in T4_TripSheet GC Template View |  | Not Working
6 | Allow roles to Delete Advances in T4 Tripsheet and Manage Trip Details |  | Not working

## Sheet3
Modules | Status | Resource worked on
Service Request |  | Akshay
jobcard parts request |  | Akshay
jobcard Delivery Demo |  | Akshay
Jobcard credit bill |  | Akshay
Jobcard Dispatch |  | Akshay
Jobcard Estimation |  | Vinutha
Jobcard Estimation Approval |  | Vinutha
Vehicle maintaenance Items |  | Vinutha
Driver Maintaenance Request |  | Vinutha
Labour Details |  | Vinutha
Inventory - Return Items |  | Vinutha
T1 flow | Comp
T2 Flow | Comp
T4 Flow | Comp
Tyre FLow | Comp
Inventory Flow | comp
Master Entry | Comp
T1 flags | Comp
T2 Flags | Comp
T4 Flags | Comp